| Date | 03 October 2026 |
| --- | --- |
| Team ID | 6ab8f5efc23107aaaa7325ec |
| Project Name | Auto Ticket Classification using Flow Designer |
| Maximum Marks | 5 Marks |

Project Planning Phase

Project Planning Template (Product Backlog, Sprint Planning, Stories, Story points)

Product Backlog, Sprint Schedule, and Estimation

| Sprint | Functional Requirement (Epic) | User Story Number | User Story / Task | Story Points | Priority | Team Members |
| --- | --- | --- | --- | --- | --- | --- |
| Sprint-1 | Core Flow & Trigger | USN-1 | As the system, when a new ticket is created I trigger the classification flow. | 3 | High | Dev 1 |
| Sprint-1 | Core Flow & Trigger | USN-2 | As the system, I extract Short Description + Description and basic ticket metadata. | 2 | High | Dev 1 |
| Sprint-1 | Rule-based Classification | USN-3 | As the system, I apply Decision Table / keyword rules for high-confidence classification. | 5 | High | Dev 2 |
| Sprint-1 | Rule-based Classification | USN-4 | As an admin, I can maintain the keyword / Decision Table entries without code changes. | 3 | High | Dev 2 |
| Sprint-1 | Ticket Update & Routing | USN-5 | As the system, I update Category, Priority, Assignment Group and write a work note. | 3 | High | Dev 1 |
| Sprint-1 | Manual Review Fallback | USN-6 | As the system, if confidence is low I route the ticket to the Manual Review queue. | 3 | High | Dev 1 |
| Sprint-1 | Audit Logging | USN-7 | As the system, I write a complete audit record for every classification decision. | 2 | High | Dev 2 |
| Sprint-2 | AI Classification | USN-8 | As the system, I call the AI / Predictive Intelligence model for tickets not handled by rules. | 5 | High | Dev 1, Dev 2 |
| Sprint-2 | AI Classification | USN-9 | As the system, I receive Category, Priority, Assignment Group and Confidence Score from the AI model. | 3 | High | Dev 1 |
| Sprint-2 | Confidence Threshold | USN-10 | As an admin, I can configure the confidence threshold that decides auto-assign vs manual review. | 2 | Medium | Dev 2 |
| Sprint-2 | Agent Feedback | USN-11 | As an agent, I can mark a classification as Correct or Incorrect from the ticket form. | 3 | Medium | Dev 1 |
| Sprint-2 | Agent Feedback | USN-12 | As the system, I store agent feedback linked to the original prediction for future improvement. | 2 | Medium | Dev 2 |
| Sprint-3 | Explainability | USN-13 | As an agent, I can see a short human-readable explanation of why a category was chosen. | 3 | Medium | Dev 1 |
| Sprint-3 | Dashboard & Monitoring | USN-14 | As a manager, I can view classification volume, average confidence, override rate and accuracy. | 5 | Medium | Dev 2 |
| Sprint-3 | Configuration & Admin | USN-15 | As an admin, I can enable/disable auto-assignment and manage multiple ticket types. | 3 | Medium | Dev 1 |
| Sprint-3 | External AI (Optional) | USN-16 | As the system, I can optionally call an external AI endpoint when platform AI confidence is low. | 5 | Low | Dev 1, Dev 2 |
| Sprint-3 | Pilot Preparation | USN-17 | As the team, I prepare pilot scope, success metrics and a small production pilot plan. | 3 | High | All |
| Sprint-3 | Documentation & Handover | USN-18 | As the team, I complete technical documentation, runbooks and knowledge transfer. | 3 | Medium | All |

Story Point Scale used: 1 (Very Easy), 2 (Normal), 3 (Moderate), 5 (Difficult) – Fibonacci-style

Sprint Summary – Story Points

| Sprint | Total Story Points | Focus |
| --- | --- | --- |
| Sprint-1 | 21 | Core Flow, Rules, Routing, Audit (MVP) |
| Sprint-2 | 15 | AI Classification, Confidence, Agent Feedback |
| Sprint-3 | 19 | Explainability, Dashboard, Optional External AI, Pilot & Docs |

Total Story Points across all sprints = 21 + 15 + 19 = 55

Project Tracker, Velocity & Burndown Chart

| Sprint | Total Story Points | Duration | Sprint Start Date | Sprint End Date (Planned) | Story Points Completed | Sprint Release Date (Actual) |
| --- | --- | --- | --- | --- | --- | --- |
| Sprint-1 | 21 | 10 Days | 06 Oct 2026 | 15 Oct 2026 | 21 (planned) | 15 Oct 2026 |
| Sprint-2 | 15 | 10 Days | 16 Oct 2026 | 25 Oct 2026 | 15 (planned) | 25 Oct 2026 |
| Sprint-3 | 19 | 10 Days | 27 Oct 2026 | 05 Nov 2026 | 19 (planned) | 05 Nov 2026 |

Velocity Calculation

Velocity = Total Story Points Completed / Number of Sprints

Assuming all planned points are completed:

Total Story Points = 55

Number of Sprints = 3

Velocity = 55 / 3 ≈ 18.3 Story Points per Sprint

Team’s planned velocity is approximately 18–19 Story Points per 10-day Sprint.

Burndown Chart (Conceptual)

A burndown chart will be maintained during each sprint showing remaining story points versus days. Ideal line starts at the sprint’s total points on Day 0 and reaches 0 on the last day. Actual progress is plotted daily. Any deviation above the ideal line indicates the team is behind schedule.

References for burndown: https://www.atlassian.com/agile/tutorials/burndown-charts

Definitions (Quick Reference)

• Sprint: A fixed period (here 10 days) in which the team completes a set of stories.

• Epic: A large body of work (e.g., Core Flow & Trigger) that is broken into multiple user stories.

• User Story: A small, valuable piece of work written from the user’s perspective.

• Story Point: Relative effort estimate (1, 2, 3, 5) – not hours.

Project: Auto Ticket Classification using Flow Designer  |  Project Planning Phase  |  Team ID: 6ab8f5efc23107aaaa7325ec